## Project schedule
| Quản lý sản phẩm | [5 empty] | Project start: | [7 empty] | 2024-10-10
Nhóm 2
[7 empty] | 2024-09-30 | [6 empty] | 2024-10-07 | [6 empty] | 2024-10-14 | [6 empty] | 2024-10-21 | [6 empty] | 2024-10-28 | [6 empty] | 2024-11-04 | [6 empty] | 2024-11-11 | [6 empty] | 2024-11-18
| Công việc | Người thực hiện | Tiến độ | Bắt đầu | Kết thúc | time axis 2024-09-30 to 2024-11-24
[7 empty] | T | T | T | T | T | T | C | T | T | T | T | T | T | C | T | T | T | T | T | T | C | T | T | T | T | T | T | C | T | T | T | T | T | T | C | T | T | T | T | T | T | C | T | T | T | T | T | T | C | T | T | T | T | T | T | C
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Giai đoạn 1: Khởi tạo và Lên kế hoạch
| Xác định mục tiêu dự án và yêu cầu hệ thống | Tất cả | 100% | 2024-10-10 | 2024-10-12 | 3
| Phân chia công việc cho các thành viên | Tất cả | 100% | 2024-10-13 | 2024-10-14 | 2
| Xác định công nghệ và nền tảng phát triển | Tất cả | 100% | 2024-10-15 | 2024-10-16 | 2
Giai đoạn 2: Phân tích và Thiết kế
| Phân tích yêu cầu chi tiết hệ thống | Khánh Phương, Hoài Linh | 100% | 2024-10-17 | 2024-10-19 | 3
| Thiết kế giao diện người dùng (UI/UX) | Mai Huyền | 100% | 2024-10-17 | 2024-10-21 | 5
| Thiết kế cơ sở dữ liệu và lưu trữ thông tin | Hoài Linh | 100% | 2024-10-17 | 2024-10-21 | 5
Giai đoạn 3: Coding (Lập trình)
| Lập trình giao diện người dùng (UI) | Khánh Phương | 80% | 2024-10-22 | 2024-10-26 | 5
| Lập trình các chức năng của admin(thêm xoá sửa) | Mai Huyền | 70% | 2024-10-22 | 2024-10-26 | 5
| Lập trình back-end và xử lý dữ liệu | Hoài Linh | 70% | 2024-10-22 | 2024-10-28 | 7
Giai đoạn 4: Đánh giá và Kiểm tra
| Kiểm tra các tính năng giao diện người dùng | Khánh Phương | 70% | 2024-10-29 | 2024-11-02 | 5
| Lập trình các chức năng của admin(thêm xoá sửa) | Mai Huyền | 60% | 2024-10-29 | 2024-11-02 | 5
| Kiểm tra hệ thống back-end và cơ sở dữ liệu | Hoài Linh | 70% | 2024-10-29 | 2024-11-02 | 5
Giai đoạn 5: Làm Slide và Viết Báo cáo
| Tạo slide thuyết trình | Mai Huyền | 60% | 2024-11-03 | 2024-11-05 | 3
| Viết báo cáo tóm tắt kết quả dự án | Khánh Phương | 50% | 2024-11-03 | 2024-11-05 | 3
| Cập nhật báo cáo và slide | Tất cả | 80% | 2024-11-06 | 2024-11-08 | 3
Giai đoạn 6: Hoàn thiện và Trình bày
| Hoàn thiện sản phẩm và chuẩn bị thuyết trình | Tất cả | 50% | 2024-11-08 | 2024-11-12 | 5
| Chỉnh sửa báo cáo và slide theo yêu cầu | Tất cả | 50% | 2024-11-13 | 2024-11-15 | 3
Giai đoạn 7: Kiểm tra cuối cùng và Triển khai
| Kiểm tra lại tất cả các tính năng và sửa lỗi | Tất cả | 40% | 2024-11-15 | 2024-11-17 | 3
| Triển khai web chính thức và kiểm tra lần cuối | Tất cả | 30% | 2024-11-19 | 2024-11-21 | 3
| Hoàn thiện và chuẩn bị báo cáo cuối cùng | Tất cả | 30% | 2024-11-22 | 2024-11-25 | 4

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.